## Gantt
Bachelor Thesis Gantt Chart (01 Feb 2026 – 01 Jun 2026)
ID | Phase | Task | Start | End | Duration (days) | Deliverable / Done when… | 01-Feb | 08-Feb | 15-Feb | 22-Feb | 01-Mar | 08-Mar | 15-Mar | 22-Mar | 29-Mar | 05-Apr | 12-Apr | 19-Apr | 26-Apr | 03-May | 10-May | 17-May | 24-May | 31-May
P1 | Setup | Accounts + access to Stoomboot GPU nodes, repo access | 2026-02-01 | 2026-02-07 | 7 | SSH works; GPU node reachable; basic GPU check OK | bar: 01-Feb
P2 | Setup | Build & run baseline (traccc build + minimal runnable example) | 2026-02-01 | 2026-02-14 | 14 | Reproducible build + baseline command documented | bar: 01-Feb to 08-Feb
P3 | Literature | Literature surveillance (SOTA + traccc/ACTS ambiguity resolution) | 2026-02-01 | 2026-02-21 | 21 | Annotated bibliography + 1–2 page summary | bar: 01-Feb to 15-Feb
P4 | Framing | Finalize problem statement, RQs, hypotheses, metrics | 2026-02-15 | 2026-02-21 | 7 | Final RQs/hypotheses + evaluation metrics | bar: 15-Feb
P5 | Baseline | Benchmarking protocol (logging, repetitions, variance) | 2026-02-15 | 2026-02-28 | 14 | Benchmark template + CSV logging | bar: 15-Feb to 22-Feb
P6 | Baseline | Baseline benchmark campaign (CPU & GPU where applicable) | 2026-02-22 | 2026-03-07 | 14 | Baseline results table + first plots | bar: 22-Feb to 01-Mar
P7 | Baseline | Profiling + bottleneck identification (ambiguity resolution) | 2026-03-08 | 2026-03-21 | 14 | Bottleneck list + evidence | bar: 08-Mar to 15-Mar
P8 | Framing | Scope lock: choose main target + fallback success criteria | 2026-03-15 | 2026-03-21 | 7 | 1-page technical spec + success criteria | bar: 15-Mar
P9 | Implementation | Prototype implementation v1 (core improvement) | 2026-03-22 | 2026-04-11 | 21 | Working code + basic tests | bar: 22-Mar to 05-Apr
P10 | Validation | Correctness harness (CPU↔GPU agreement + regression tests) | 2026-03-29 | 2026-04-18 | 21 | Automated correctness checks | bar: 29-Mar to 12-Apr
P11 | Validation | Determinism study + implementation (stable tie-breaking / repeatability) | 2026-04-12 | 2026-04-26 | 15 | Deterministic mode + quantified overhead | bar: 12-Apr to 26-Apr
P12 | Implementation | Performance iteration / optimization (incl. SoA if used) | 2026-04-12 | 2026-04-30 | 19 | Measurable improvement on ≥1 key metric | bar: 12-Apr to 26-Apr
M1 | Milestone | Language Centre draft submission | 2026-05-01 | 2026-05-01 | 1 | Draft submitted (language/structure) | bar: 26-Apr
P13 | Evaluation | Full evaluation campaign (scaling, memory, final plots) | 2026-05-01 | 2026-05-10 | 10 | Final plots/tables + regime explanation | bar: 26-Apr to 10-May
M2 | Milestone | Bachelor thesis checkpoint (meeting with both examiners) | 2026-05-11 | 2026-05-15 | 5 | Slides + status summary prepared | bar: 10-May
P14 | Writing | Writing & integration (ongoing, results integrated) | 2026-04-01 | 2026-05-24 | 54 | Coherent draft with figures | bar: 29-Mar to 24-May
P15 | Writing | Incorporate Language Centre feedback (when received) | 2026-05-12 | 2026-05-24 | 13 | Revised clarity/structure | bar: 10-May to 24-May
M3 | Milestone | First full version to supervisors | 2026-05-25 | 2026-05-25 | 1 | Full thesis sent to supervisors | bar: 24-May
P16 | Writing | Final revisions + polishing | 2026-05-26 | 2026-05-31 | 6 | Final version ready | bar: 24-May to 31-May
M4 | Milestone | Final submission (Canvas + examiners + coordinator) | 2026-06-01 | 2026-06-01 | 1 | Final PDF submitted | bar: 31-May